## Sheet1
Feature ID | Feature Name | Priority | Status | Objective | Business / Product Value | User Value | CoreRelm Alignment | Why CoreRelm Should Implement It | Scope Summary | Key Dependencies | Major Risks | TDD Test Suite First? | Acceptance Criteria | Out of Scope (initially) | Recommended Phase
CR-001 | Migration Rollback / Down Migrations | P1 | Planned | Add first-class reversal support for migrations | Makes migrations feel production-grade and safer to adopt | Users gain confidence that schema changes are not one-way only | Strongly aligned with CoreRelm’s migration/planning/rendering role | CoreRelm already owns schema comparison, operation planning, SQL rendering, checksum/header logic, and status/drift; rollback is a natural extension of that migration system. | Reversible operations model, down-plan generation, SQL rendering, metadata/tests | Existing migration planner/renderer/header/checksum infrastructure | Non-reversible operations, data-loss ambiguity, provider-specific reversal rules | Yes | Green test suite covering reversible and non-reversible scenarios; generated down SQL is deterministic; rollback metadata and status behavior are defined | Arbitrary data restoration, cross-provider parity, automatic rollback execution orchestration in host app | Phase 1
CR-002 | Transactions API / Ergonomics | P2 | Planned | Provide explicit, clean transactional control for multi-step operations | Reduces runtime risk and improves production readiness | Users can safely bundle writes and recover on failure | Strongly aligned with RelmContext / core data-access experience | Transaction support is a core ORM expectation and fits CoreRelm’s explicit/predictable style better than hidden behavior | Public transaction surface, nesting rules, async usage, error behavior | RelmContext / database work internals | Inconsistent semantics, connection lifecycle issues, nested transaction complexity | Yes | Tests define success, rollback, nested behavior, async flow, disposal/error semantics | Distributed transactions | Phase 2
CR-003 | Optimistic Concurrency | P3 | Planned | Prevent silent lost updates in concurrent modification scenarios | Increases trust for real application workloads | Users get predictable conflict detection instead of silent overwrites | Good fit with production-grade ORM behavior | CoreRelm appears intended for serious app usage, so a minimal explicit concurrency model would materially improve safety | Version token model, update checks, exceptions/result states | Persistence/update pipeline | Complex mapping rules, backward compatibility, provider differences later | Yes | Tests prove stale-write detection, token updates, and clean behavior when concurrency is disabled | Full conflict resolution workflows | Phase 3
CR-004 | Diagnostics / Logging / Interception | P4 | Planned | Make ORM behavior visible and debuggable | Improves supportability, adoption, and trust | Users can inspect SQL, timings, failures, migration behavior | Strongly aligned with deterministic/professional tooling goals | CoreRelm already has structured migration planning/rendering/status concepts; diagnostics makes that professionalism visible | SQL logging, migration diagnostics, timings, hooks/interceptors | Execution pipeline and migration pipeline | Noise, sensitive-data exposure, poor API shape | Yes | Tests verify events/hooks fire correctly, are ordered correctly, and can be configured safely | Full tracing ecosystem integrations | Phase 4
CR-005 | Query Ergonomics | P5 | Candidate | Improve expressive, strongly typed querying | Better adoption and day-to-day developer usability | Users can query without dropping down too often to lower-level mechanisms | Aligned, but should be approached carefully | Valuable, but should not distract from the stronger “correctness + migrations + safety” foundation first | Query composition improvements, filtering/projection/paging helpers | Existing context/query internals | Over-design, LINQ-clone trap, API sprawl | Yes | Tests define query shapes, translation/output, parameterization, and invalid cases | Full LINQ replacement | Later
CR-006 | Relationship Loading Ergonomics | P6 | Candidate | Make related-entity loading easier and clearer | Better developer experience for relational apps | Easier graph loading and explicit navigation handling | Good fit with FK-heavy ORM use | CoreRelm already has FK concepts; better ergonomics would polish an existing strength | Explicit/eager loading patterns, collection handling | FK metadata and query/load internals | Hidden N+1 behavior, ambiguity | Yes | Tests define explicit loading behavior and prevent hidden unexpected DB calls | Lazy loading | Later
CR-007 | Seed / Bootstrap Data | P7 | Candidate | Provide a standard way to manage baseline/reference data | Improves app bootstrap and test/dev consistency | Easier environment setup | Moderately aligned | Useful after migrations mature, but less foundational than rollback/transactions | Seed declarations or seed scripts, idempotent behavior | Migration/runtime boundaries | Hidden side effects, scope creep into app orchestration | Yes | Tests prove deterministic and idempotent behavior | Full environment orchestration | Later
CR-008 | Reverse Engineering / Scaffolding | P8 | Candidate | Generate model/mapping artifacts from existing DB schema | Helps adoption in brownfield systems | Easier onboarding for existing databases | Strategically aligned with future generic internals | CoreRelm already has schema introspection, making this a natural eventual extension. | Schema-to-model generation, baseline generation | Introspection system | Incomplete mapping fidelity, provider variance | Yes | Tests validate deterministic scaffolding output for known schemas | Full visual designer | Later